|  | 11/4/2008 |  |
| --- | --- | --- |
|  | Bilkent University Team 6 Özgün ÇITLAK Çiğdem ARDAHAN Kıraç SÖĞÜTLÜ Arda KART Altuğ ZAİMOĞLU Ege GÖRGÜLÜ |  |

[weekly report iV] Project Name: vtravel - Travel help for visually impaired people

The document contains the last week’s achievements and the goals for the next week.

# Project: vTravel

Overall status: Green

# Past Week’s Accomplishments

Dates between: October 21, 2008 – November 3, 2008

- Preliminary design document, weekly report and weekly assessment sheet submitted.

- Worked on preparing the development plan.

- Possible cost reduction methods are discussed.

In the meeting where we discussed what to put into ‘Development Plan’, every member of our group contributed with their ideas. After discussing how to write the document the team decided each member to write his part of the document and Arda Kart to merge the units. We divided the remaining main topics below between our members:

- Ozgun Citlak and Cigdem Ardahan: Prepared part of the development plan concerning the engineering and testing parts of the product in a detailed way.

- Arda Kart and Altug Zaimoglu: Prepared part of the development plan concerning the production, component ordering and quality checking parts of the product.

- Kirac Sogutlu: Prepared part of the development plan concerning the finances of product.

- Ege Gorgulu: Prepared part of the development plan concerning the visual parts of the product.

# Next Week’s Goals

Dates between: November 4, 2008 – November 10, 2008

- Discussions on components and part design.

- Discussions on how to allocate financial resources

- Discussion on component ordering.

- Making a domain analysis for navigation systems and preparing use case scenarios for the product

- Making a survey on expected costs of the product

# Duty Allocation

| Schedule item | Item Owner | Plan date | Estimated Completion Date | Actual or scheduled | Comments |
| --- | --- | --- | --- | --- | --- |
| Project and Production Plan | Cigdem Ardahan | 10/6/2008 | 10/10/2008 | 11/1/2008 | Complete: Included as part of Dev. plan |
| Part Design Strategy | Altug Zaimoglu | 10/6/2008 | 10/11/2008 | - | Suspended |
| Web Site Design | Ege Gorgulu | 10/6/2008 | 10/12/2008 | - | Suspended |
| Making a survey on subassemblies | Arda Kart | 10/20/2008 | 11/1/2008 | 10/31/2008 | Complete |
| Ideas about how to reduce the cost | Altug Zaimoglu | 10/20/2008 | 10/30/2008 | 11/1/2008 | Complete |
| Development plan for engineering and testing | Ozgun Citlak | 10/20/2008 | 11/2/2008 | 11/3/2008 | Complete |
| Development plan for engineering and maintenance | Cigdem Ardahan | 10/20/2008 | 11/2/2008 | 11/3/2008 | Complete |
| Development plan for marketing and finances | Kirac Sogutlu | 10/20/2008 | 11/1/2008 | 10/31/2008 | Complete |
| Development plan for production and quality management | Arda Kart | 10/20/2008 | 11/1/2008 | 11/1/2008 | Complete |
| Development plan for production and quality management | Altug Zaimoglu | 10/20/2008 | 11/1/2008 | 10/31/2008 | Complete |
| Development plan for marketing and visuality | Ege Gorgulu | 10/20/2008 | 11/1/2008 | 11/1/2008 | Complete |
| Making a domain analysis for navigation software | Cigdem Ardahan | 11/4/2008 | 11/9/2008 | - | In Progress |
| Preparing use case scenarios for product | Ozgun Citlak | 11/4/2008 | 11/10/2008 | - | In Progress |
| Survey on expected costs | Altug Zaimoglu | 11/4/2008 | 11/10/2008 | - | In Progress |
| Survey on expected costs | Arda Kart | 11/4/2008 | 11/9/2008 | - | In Progress |
| Expenditure allocation | Kirac Sogutlu | 11/4/2008 | 11/10/2008 | - | In Progress |
| Preparing initial images for product | Ege Gorgulu | 11/4/2008 | 11/13/2008 | - | In Progress |

Explanation about the comments:

- Completed duties (marked with “Complete”) will NOT be listed in next week’s weekly report.

- Suspended duties (marked with “Suspended”) will be listed in the weekly reports until they are fulfilled or dismissed permanently. Explanation will be given only at the week it is suspended.

- If a work is “In Progress”, then someone is working on it and it is not yet complete. Therefore, these duties are still assigned to the “Item Owner” for the upcoming week and it is not listed on a new line.