|  | 11/18/2008 |  |
| --- | --- | --- |
|  | Bilkent University Team 6 Özgün ÇITLAK Çiğdem ARDAHAN Kıraç SÖĞÜTLÜ Arda KART Altuğ ZAİMOĞLU Ege GÖRGÜLÜ |  |

[WEEKLY REPORT VI] Project Name: vtravel - Travel help for visually impaired people

The document contains the last week’s achievements and goals for the next week.

# Project: vTravel

Overall status: Yellow†

# Past Week’s Accomplishments

Dates between: November 11, 2008 – November 17, 2008

- Product and Subassembly Specification, weekly report and weekly assessment sheet submitted.

- Worked on preparing expenditure plan.

- Possible cost reduction methods are discussed.

- Prepared sequence diagrams for the system.

In the meeting we discussed what to put into expenditure plan. After discussing how to write the document, we divided the work among our members and the team decided each member to write his part of the document and Ozgun Citlak to merge the units. Individual works of our members:

- Ozgun Citlak and Cigdem Ardahan: Prepared sequence diagrams and Ozgun also researched how to record mp3 files.

- Arda Kart and Altug Zaimoglu: Worked on expected costs.

- Kirac Sogutlu: Worked on the expenditure planning.

- Ege Gorgulu: Worked on initial images of the product.

# Next Week’s Goals

Dates between: November 18, 2008 – November 24, 2008

- Discuss how to divide topics for Business plan

- Preparing presentation about the works accomplished.

- Finalize discussions about the components to buy and ordering them.

- Start preparing domain model for the product.

- Finish preparing sequence diagrams for the product.

# Duty Allocation

| Schedule item | Item Owner | Plan date | Estimated Completion Date | Actual or scheduled | Comments |
| --- | --- | --- | --- | --- | --- |
| Web Site Design | Ege Gorgulu | 10/6/2008 | 10/12/2008 | - | Suspended |
| Survey on expected costs | Altug Zaimoglu | 11/4/2008 | 11/16/2008 | 11/17/2008 | Complete |
| Survey on expected costs | Arda Kart | 11/4/2008 | 11/16/2008 | 11/17/2008 | Complete |
| Expenditure allocation | Kirac Sogutlu | 11/4/2008 | 11/16/2008 | 11/17/2008 | Complete |
| Preparing initial images for product | Ege Gorgulu | 11/4/2008 | 11/16/2008 | - | In Progress: since last two weeks |
| Preparing sequence diagrams for product | Cigdem Ardahan | 11/11/2008 | 11/20/2008 | - | In Progress since last week (75%) |
| Preparing sequence diagrams for product | Ozgun Citlak | 11/11/2008 | 11/20/2008 | - | In Progress since last week (75%) |
| Researching about recording mp3 files | Ozgun Citlak | 11/11/2008 | 11/21/2008 | 11/17/2008 | Complete |
| Preparing domain model for product | Cigdem Ardahan | 11/18/2008 | 12/8/2008 | - | In Progress |
| Preparing domain model for product | Ozgun Citlak | 11/18/2008 | 12/8/2008 | - | In Progress |
| Ordering components | Altug Zaimoglu | 11/18/2008 | 11/24/2008 | - | In Progress |
| Ordering components | Arda Kart | 11/18/2008 | 11/24/2008 | - | In Progress |
| Investigating parts of Business plan | Kirac Sogutlu | 11/18/2008 | 11/24/2008 | - | In Progress |

Explanation about the comments:

- Completed duties (marked with “Complete”) will NOT be listed in next week’s weekly report.

- Suspended duties (marked with “Suspended”) will be listed in the weekly reports until they are fulfilled or dismissed permanently. Explanation will be given only at the week it is suspended.

- If a work is “In Progress”, then someone is working on it and it is not yet complete. Therefore, these duties are still assigned to the “Item Owner” for the upcoming week and it is not listed on a new line.  The percentage inside parenthesis is the completion percentage of that activity.

# Footnotes

† Ordering of Nokia Tablet has been delayed to next week, which increases the critical path time by at least 2 weks.