|  | 11/25/2008 |  |
| --- | --- | --- |
|  | Bilkent University Team 6 Özgün ÇITLAK Çiğdem ARDAHAN Kıraç SÖĞÜTLÜ Arda KART Altuğ ZAİMOĞLU Ege GÖRGÜLÜ |  |

[WEEKLY REPORT VIi] Project Name: vtravel - Travel help for visually impaired people

The document contains the last week’s achievements and goals for the next week.

# Project: vTravel

Overall status: Yellow†

# Past Week’s Accomplishments

Dates between: November 18, 2008 – November 24, 2008

- Expenditure plan, weekly report and weekly assessment sheet submitted.

- Worked on preparing the presentation.

- Possible cost reduction methods are discussed.

- Prepared sequence diagrams for the system.

In the meeting we discussed what to put into presentation. After discussing what to include, we divided the work among our members and the team decided each member to write his part of the document and Ege Gorgulu to prepare the final presentation file. Individual works of our members:

- Ozgun Citlak: Prepared his part of the presentation.

- Cigdem Ardahan: Prepared her part of the presentation.

- Arda Kart: Prepared his part of the presentation.

- Altug Zaimoglu: Prepared his part of the presentation.

- Kirac Sogutlu: Prepared his part of the presentation.

- Ege Gorgulu: Designed the layout for the presentation. Prepared his part of the presentation.

# Next Week’s Goals

Dates between: November 25, 2008 – December 2, 2008

- Discuss how to divide topics for Business plan

- Preparing presentation about the works accomplished.

- Finalize discussions about the components to buy and ordering them.

- Start preparing domain model for the product.

- Finish preparing sequence diagrams for the product.

# Duty Allocation

| Schedule item | Item Owner | Plan date | Estimated Completion Date | Actual or scheduled | Comments |
| --- | --- | --- | --- | --- | --- |
| Web Site Design | Ege Gorgulu | 10/6/2008 | 10/12/2008 | - | Suspended |
| Preparing initial images for product | Ege Gorgulu | 11/4/2008 | 11/16/2008 | - | In Progress: since last three weeks |
| Preparing sequence diagrams for product | Cigdem Ardahan | 11/11/2008 | 11/20/2008 | 11/23/2008 | Complete |
| Preparing sequence diagrams for product | Ozgun Citlak | 11/11/2008 | 11/20/2008 | 11/23/2008 | Complete |
| Preparing domain model for product | Cigdem Ardahan | 11/18/2008 | 12/8/2008 | - | In Progress: since last week |
| Preparing domain model for product | Ozgun Citlak | 11/18/2008 | 12/8/2008 | - | In Progress: since last week |
| Ordering components | Altug Zaimoglu | 11/18/2008 | 11/30/2008 | - | In Progress: since last week |
| Ordering components | Arda Kart | 11/18/2008 | 11/30/2008 | - | In Progress: since last week |
| Investigating parts of Business plan | Kirac Sogutlu | 11/18/2008 | 11/24/2008 | 11/24/2008 | Complete |
| Marketing plan | Kirac Sogutlu | 11/18/2008 | 11/30/2008 | - | In Progress |

Explanation about the comments:

- Completed duties (marked with “Complete”) will NOT be listed in next week’s weekly report.

- Suspended duties (marked with “Suspended”) will be listed in the weekly reports until they are fulfilled or dismissed permanently. Explanation will be given only at the week it is suspended.

- If a work is “In Progress”, then someone is working on it and it is not yet complete. Therefore, these duties are still assigned to the “Item Owner” for the upcoming week and it is not listed on a new line.  The percentage inside parenthesis is the completion percentage of that activity.

# Footnotes

† Ordering of Nokia Tablet has been delayed to next week, which increases the critical path time by at least 2 weeks.